## Project Timeline 2022
PROJECT TIMELINE TEMPLATE
AT RISK | TASK NAME | DETAILS | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
| Form committee and subcommittees |  | Complete | PC | 2021-11-01 | 2021-11-30 | 29 | Planning Committee = PC, Venue Subcommittee = VSC, Program Subcommittee = PSC, Budget Subcommittee = BSC
| Contact potential vendors | Illumina, KU GSC | Complete | BSC | 2021-11-01 | 2021-11-30 | 29 | Illumina - (contact: Katie Brunetti) Paid for breakfast, gave a talk, provided lanyards, GSC - (contact: Jennifer Hackett) had a table
| Nominate and pick keynote and backup |  | Complete | PC, PSC | 2021-11-01 | 2021-12-21 | 50
| Decide on symposium size, dates, and deadlines | Symposium date, abstract submission deadlines, registration deadlines | Complete | PC | 2021-12-01 | 2022-01-15 | 45 | Avoid local college and public school graduation dates
| Pick venue and reserve date |  | Complete | VSC, BSC | 2021-12-15 | 2022-01-15 | 31 | Request a quote, consider breakfast and lunch menu options, coffee/tea service, space for talks and posters
| Send Keynote invitation |  | Complete | PSC | 2022-01-05 | 2022-01-15 | 10
| Organize poster tripods and boards | KU HBC | Complete | PSC | 2022-01-05 | 2022-01-31 | 26 | 35 posters fit tightly in Maceli's front room
| Plan use of venue space |  | Complete | VSC, PSC | 2022-01-15 | 2022-05-18 | 123
| Organize Keynote travel and lodging |  | Complete | PSC | 2022-01-15 | 2022-02-01 | 17 | Coordinate with keynote and kucr for travel expenses and reservations
| Determine cap for posters and talks |  | Complete | PSC, PC | 2022-02-01 | 2022-02-06 | 5
| Make a webpage for symposium information and registration |  | Complete | PC | 2022-02-01 | 2022-02-15 | 14
| Finalize registration page, finalize deadlines |  | Complete | PC | 2022-02-01 | 2022-02-28 | 27
| Generate a draft program |  | Complete | PSC | 2022-02-01 | 2022-02-28 | 27
| Send symposium announcement email | KU MB, EEB; KUMC, Stowers, UMKC, KSU, OSU, OU, EvolDir, tweet | Complete | kucg@ku.edu | 2022-03-01 | 2022-03-07 | 6
| Send symposium reminder email | KU MB, EEB; KUMC, Stowers, UMKC, KSU, OSU, OU, EvolDir, tweet | Complete | kucg@ku.edu | 2022-04-01 | 2022-04-07 | 6
| Organize photographer |  | Complete | BSC | 2022-04-01 | 2022-04-30 | 29
| Send registration deadline reminder email | KU MB, EEB; KUMC, Stowers, UMKC, KSU, OSU, OU, EvolDir, tweet | Complete | kucg@ku.edu | 2022-04-19 | 2022-04-21 | 2
| Assign backup speakers from PC |  | Complete | PC | 2022-04-20 | 2022-04-30 | 10
| Plan keynote schedule | transportation to venue, dinner | Complete | PC, BSC | 2022-04-20 | 2022-05-10 | 20
| Publish program on website |  | Complete | PSC | 2022-05-01 | 2022-05-07 | 6
| Organize logistics information | parking, venue address, hotes, dinner options, map | Complete | VSC | 2022-05-01 | 2022-05-07 | 6
| Confirm oral presenations |  | Complete | PSC | 2022-05-01 | 2022-05-07 | 6
| Send symposium information email | attendees | Complete | kucg@ku.edu | 2022-05-01 | 2022-05-07 | 6
| Assign poster numbers and post to website |  | Complete | PSC | 2022-05-01 | 2022-05-10 | 9
| Finalize keynote dinner reservations |  | Complete | BSC, PSC | 2022-05-01 | 2022-05-15 | 14
| Obtain W9 and contractual agreement from keynote |  | Complete | PSC | 2022-05-01 | 2022-05-15 | 14 | for paying honorarium
| Create and finalize feedback survey |  | Complete | PSC | 2022-05-01 | 2022-05-15 | 14
| Identify judges for posters and talks |  | Complete | PC | 2022-05-07 | 2022-05-15 | 8
| Assign day of duties |  | Complete | PC | 2022-05-07 | 2022-05-19 | 12
| Print and stuff name tags |  | Complete | PSC | 2022-05-07 | 2022-05-19 | 12
| Send schedule to keynote |  | Complete | PSC | 2022-05-15 | 2022-05-16 | 1
| Order and pick up giant checks and program books |  | Complete | PSC | 2022-05-15 | 2022-05-19 | 4
| Set up Zoom link for virtual attendees |  | Complete | kucg@ku.edu | 2022-05-15 | 2022-05-19 | 4
| Judge posters and tally semi final scores |  | Complete | PC | 2022-05-17 | 2022-05-19 | 2
| Send final symposium email with Zoom link | attendees | Complete | kucg@ku.edu | 2022-05-18 | 2022-05-19 | 1
| Set up venue space | poster tripods and boards, registration tables, test microphones, projector | Complete | PC | 2022-05-18 | 2022-05-19 | 1
| Symposium |  | Complete | PC | 2022-05-20 | 2022-05-21 | 1
| Send thank you and survey email | attendees | Complete | kucg@ku.edu | 2022-05-21 | 2022-05-23 | 2
| Disburse money to winners |  | Complete | PC | 2022-05-21 | 2022-05-25 | 4

## Project Timeline 2023
PROJECT TIMELINE TEMPLATE
AT RISK | TASK NAME | DETAILS | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
| Form committee and subcommittees |  | Complete | PC | 2021-11-01 | 2021-11-30 | 29 | Planning Committee = PC, Venue Subcommittee = VSC, Program Subcommittee = PSC, Budget Subcommittee = BSC
| Contact potential vendors | Illumina, KU GSC | Complete | BSC | 2021-11-01 | 2021-11-30 | 29 | Illumina - (contact: Katie Brunetti) Paid for breakfast, gave a talk, provided lanyards, GSC - (contact: Jennifer Hackett) had a table
| Nominate and pick keynote and backup |  | Complete | PC, PSC | 2021-11-01 | 2021-12-21 | 50
| Decide on symposium size, dates, and deadlines | Symposium date, abstract submission deadlines, registration deadlines | Complete | PC | 2021-12-01 | 2022-01-15 | 45 | Avoid local college and public school graduation dates
| Pick venue and reserve date |  | Complete | VSC, BSC | 2021-12-15 | 2022-01-15 | 31 | Request a quote, consider breakfast and lunch menu options, coffee/tea service, space for talks and posters
| Send Keynote invitation |  | Complete | PSC | 2022-01-05 | 2022-01-15 | 10
| Organize poster tripods and boards | KU HBC | Complete | PSC | 2022-01-05 | 2022-01-31 | 26 | 35 posters fit tightly in Maceli's front room
| Plan use of venue space |  | Complete | VSC, PSC | 2022-01-15 | 2022-05-18 | 123
| Organize Keynote travel and lodging |  | Complete | PSC | 2022-01-15 | 2022-02-01 | 17 | Coordinate with keynote and kucr for travel expenses and reservations
| Determine cap for posters and talks |  | Complete | PSC, PC | 2022-02-01 | 2022-02-06 | 5
| Make a webpage for symposium information and registration |  | Complete | PC | 2022-02-01 | 2022-02-15 | 14
| Finalize registration page, finalize deadlines |  | Complete | PC | 2022-02-01 | 2022-02-28 | 27
| Generate a draft program |  | Complete | PSC | 2022-02-01 | 2022-02-28 | 27
| Send symposium announcement email | KU MB, EEB; KUMC, Stowers, UMKC, KSU, OSU, OU, EvolDir, tweet | Complete | kucg@ku.edu | 2022-03-01 | 2022-03-07 | 6
| Send symposium reminder email | KU MB, EEB; KUMC, Stowers, UMKC, KSU, OSU, OU, EvolDir, tweet | Complete | kucg@ku.edu | 2022-04-01 | 2022-04-07 | 6
| Organize photographer |  | Complete | BSC | 2022-04-01 | 2022-04-30 | 29
| Send registration deadline reminder email | KU MB, EEB; KUMC, Stowers, UMKC, KSU, OSU, OU, EvolDir, tweet | Complete | kucg@ku.edu | 2022-04-19 | 2022-04-21 | 2
| Assign backup speakers from PC |  | Complete | PC | 2022-04-20 | 2022-04-30 | 10
| Plan keynote schedule | transportation to venue, dinner | Complete | PC, BSC | 2022-04-20 | 2022-05-10 | 20
| Publish program on website |  | Complete | PSC | 2022-05-01 | 2022-05-07 | 6
| Organize logistics information | parking, venue address, hotes, dinner options, map | Complete | VSC | 2022-05-01 | 2022-05-07 | 6
| Confirm oral presenations |  | Complete | PSC | 2022-05-01 | 2022-05-07 | 6
| Send symposium information email | attendees | Complete | kucg@ku.edu | 2022-05-01 | 2022-05-07 | 6
| Assign poster numbers and post to website |  | Complete | PSC | 2022-05-01 | 2022-05-10 | 9
| Finalize keynote dinner reservations |  | Complete | BSC, PSC | 2022-05-01 | 2022-05-15 | 14
| Obtain W9 and contractual agreement from keynote |  | Complete | PSC | 2022-05-01 | 2022-05-15 | 14 | for paying honorarium
| Create and finalize feedback survey |  | Complete | PSC | 2022-05-01 | 2022-05-15 | 14
| Identify judges for posters and talks |  | Complete | PC | 2022-05-07 | 2022-05-15 | 8
| Assign day of duties |  | Complete | PC | 2022-05-07 | 2022-05-19 | 12
| Print and stuff name tags |  | Complete | PSC | 2022-05-07 | 2022-05-19 | 12
| Send schedule to keynote |  | Complete | PSC | 2022-05-15 | 2022-05-16 | 1
| Order and pick up giant checks and program books |  | Complete | PSC | 2022-05-15 | 2022-05-19 | 4
| Set up Zoom link for virtual attendees |  | Complete | kucg@ku.edu | 2022-05-15 | 2022-05-19 | 4
| Judge posters and tally semi final scores |  | Complete | PC | 2022-05-17 | 2022-05-19 | 2
| Send final symposium email with Zoom link | attendees | Complete | kucg@ku.edu | 2022-05-18 | 2022-05-19 | 1
| Set up venue space | poster tripods and boards, registration tables, test microphones, projector | Complete | PC | 2022-05-18 | 2022-05-19 | 1
| Symposium |  | Complete | PC | 2022-05-20 | 2022-05-21 | 1
| Send thank you and survey email | attendees | Complete | kucg@ku.edu | 2022-05-21 | 2022-05-23 | 2
| Disburse money to winners |  | Complete | PC | 2022-05-21 | 2022-05-25 | 4

## Project Timeline - BLANK
PROJECT TIMELINE TEMPLATE
AT RISK | TASK NAME | SUB TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*