## Timeline
Date Completed | Description | File Name and Location | Notes
2022-11-01 | Form committee and subcommittees: Venue, Program, Budget
2022-11-17 | Contact Illumina to cover breakfast and send lanyards |  | Confirmed May 6
2022-11-17 | Contact KU Genome Sequencing Core to have a table and poster
2022-12-21 | Keynote and second speaker pick made | 2022_Symposium/Keynote_Speaker/InvitedSpeaker_CandidateList.csv
2022-01-01 | Decide on conference size, dates, and deadlines
2022-01-11 | Symposium date picked
2022-01-19 | Venue picked and date reserved | 2022_Symposium/General_Information/Macelis_Quote_011922.pdf
2022-01-19 | Begin planning use of venue space |  | Registration tables, vendor tables, posters, presentation podium, screen, light control, coffee/tea area, buffet area,
2022-01-20 | Keynote invitation sent | 2022_Symposium/Keynote_Speaker/KUCG_Keynote_Invite_Template.docx
2022-01-24 | Keynote accepted invitation
| Organize Keynote travel and lodging ASAP | 2022_Symposium/Keynote_Speaker/Requested_Keynote_Info.docx, Keynote_Coordinating_Contact_Info.docx | Update necessary forms (W9, contractual agreement) to pay honorarium
2022-01-28 | Poster boards organized from HBC |  | Includes tripods and tri-fold poster boards.
2022-02-01 | Determine cap for posters and talks |  | 35 posters was cramped in the front room of macelis; 15 12 min talks, 1 45 min keynote
2022-02-15 | Make a webpage for information and registration |  | Rylie Koester contact for website, established contact email for attendees: kucg@ku.edu
2022-02-21 | Registration page finalized, Deadlines finalized | 2022_Symposium/General_Information/Registration_Questions.docx | FUTURE: Add option to add additional authors
2022-02-24 | Program draft complete | 2022_Symposium/General_Information/KUCG_program.xlsx | FUTURE: break up last session
2022-03-07 | Symposium Announcement Email | 2022_Symposium/Email_Templates/SymposiumAnnouncement.docx; 2022_Symposium/General_Information/SymposiumFlyer.pdf
2022-03-14 | Advertise Symposium to EvolDir | 2022_Symposium/Email_Templates/SymposiumAnnouncement.docx; 2022_Symposium/General_Information/SymposiumFlyer.pdf
2022-03-26 | Advertise Symposium to Stowers, UMKC, KUMC, KSU | 2022_Symposium/Email_Templates/SymposiumAnnouncement.docx; 2022_Symposium/General_Information/SymposiumFlyer.pdf
2022-04-04 | Deadline to submit talks
2022-04-05 | Symposium Reminder Email | no template
2022-04-11 | Deadline to submit Posters and talks |  | talk deadline extended
2022-04-19 | Deadline to vote for selected talks | 2022_Symposium/Talks/TalkAbstracts_Voting.xlsx
2022-04-20 | Symposium registration deadline reminder email | 2022_Symposium/Email_Templates/DeadlineReminder.docx
2022-04-22 | Abstract acceptance email | 2022_Symposium/Email_Templates/AcceptanceEmails.docx
2022-04-25 | Assign backup speakers
2022-04-29 | Plan keynote schedule, identify people to have meals with keynote | 2022_Symposium/Keynote_Speaker/Schedule.xlsx
2022-04-29 | Organize photographer |  | needs to be done earlier if hiring a professional
2022-04-29 | Poster and talk judging rubrics | 2022_Symposium/Posters/Symposium_poster_rubric_QRcode.docx; 2022_Symposium/Talks/Symposium_talk_rubric_QRcode.xlsx
2022-05-04 | Program published on KUCG Website
2022-05-04 | Info on parking, venue, hotels, dinner materials put together | 2022_Symposium/General_Information/KUCG_2022Symposium_InfoSheet.pdf; 2022_Symposium/General_Information/MAP_README.txt | https://www.google.com/maps/d/edit?mid=17FpfHEpCU7kBEufgJ51hLnZdrS3GsYw&usp=sharing
2022-05-06 | Confirm all oral presentations |  | Instruct presenters to send slides to a dropbox folder for preupload
2022-05-09 | Symposium Information email | 2022_Symposium/Email_Templates/SymposiumInformation.docx; 2022_Symposium/General_Information/KUCG_2022Symposium_InfoSheet.pdf
2022-05-11 | Assign poster numbers and post to website | 2022_Symposium/Posters/KUCG_Posters_051122.docx; 2022_Symposium/Posters/KUCG_Poster_Numbers.xlsx
2022-05-13 | Finalize keynote dinner reservations |  | Thursday: Zen Zero; Friday: Merchant's
2022-05-13 | W9 and KUCR contractural services forms emailed to keynote | 2022_Symposium/Keynote_Speaker/IRS_W9.pdf, kucr-contractural-services-form-072621.pdf | Check that forms don't need to be updated; contact Christopher Anderson accounting specialist to coordinate ahead of time
2022-05-13 | Finalize feedback survey | 2022_Symposium/Post_Symposium_Survey/KUCG_symposium_survey_final.docx
2022-05-13 | Identify judges for posters and talks
2022-05-13 | Assign DAY OF duties (see below)
2022-05-13 | Print and stuff nametags | 2022_Symposium/General_Information/Avery8521VerticalStyleNameBadges_KUGC_2022.doc
2022-05-16 | Final schedule to keynote speaker | 2022_Symposium/Keynote_Speaker/Schedule.xlsx
2022-05-16 | Ordered giant checks and abstract books - FEDEX | 2022_Symposium/General_Information/GiantCheck.pdf; 2022_Symposium/General_Information/KUCG_Program_Normal.pdf | KU discount available, picked up 17-May
2022-05-18 | Set up Zoom link for virtual attendees
2022-05-19 | Judge posters and tally semi final scores | 2022_Symposium/Posters/Symposium_poster_rubric_QRcode.docx; 2022_Symposium/Posters/PosterJudging_Prelim.xlsx | Poster pdfs were submitted and viewed here prior to the symposium for judging: https://kansas-my.sharepoint.com/:f:/g/personal/j041p522_home_ku_edu/Er__M_47NX1OjAE67D6EbywB04C2mn7tzG7dtadjfioXlQ?e=vF3ytc
2022-05-19 | Final Symposium Information email | 2022_Symposium/Email_Templates/SymposiumFinalInformation.docx; 2022_Symposium/General_Information/KUCG_Program_Normal.pdf
2022-05-19 | Finalize space and set up poster tripods, registration tables, etc. (see below)
2022-05-22 | Thank you and survey email | 2022_Symposium/Email_Templates/ThankYou_Survey.docx; 2022_Symposium/General_Information/KUCG_symposium_survey_final.docx
2022-05-22 | Disburse award money to winners
2022-05-20 | DAY OF duties:
| Registration desk | Kristine, Lauren, Nichole
| Emcee/Timekeeper/Q&A moderator | Wen-Juan (1st half), Lauren (2nd half)
| Zoom moderator (muting, Q&A) | Elizabeth (1st half), Kristine (2nd half)
| Speaker computer/slide setup | Jessie
| Speaker questions/concerns | Jessie, Nichole
| Poster questions/concerns | David
| Maceli's point person | Justin
| Poster judging committee | Justin, David, Patrick, Nichole
| Talk judging committee | Elizabeth, Kristine, Lauren, Wen-Juan
| Wild card judge | Jessie
| Keynote morning escort | Rob
| Friday dinner, keynote escort | Nichole, Justin, David, Jessie, Maggie Wagner
| Saturday breakfast | Rob
DAY OF materials:
Presenter computer
Zoom computer
purell bottles
nametag holders
green lanyards for organizers
surgical masks
push pins
colored paper for timekeeping
poster numbers (printed and cut)
pens, sharpies
backup sticker nametags
| Copies of speaker guide | 2022_Symposium/General_Information/Speaker_Guide.docx
| Copies of talk rubric | 2022_Symposium/Talks/Symposium_talk_rubric_QRcode.xlsx
Index of Files | Description | File Name and Location
Email | Acceptance email sent to symposium participants | 2022_Symposium/Email_Templates/AcceptanceEmails.docx
| Deadline reminder to register for the symposium | 2022_Symposium/Email_Templates/DeadlineReminder.docx
| Email to venue to initate planning | 2022_Symposium/Email_Templates/Generic_Initial_Venue_Correspondence_060722.docx
| Keynote invitation to speak | 2022_Symposium/Email_Templates/KUCG_Keynote_Invite_Template.docx
| Initial announcement of the symposium | 2022_Symposium/Email_Templates/SymposiumAnnouncement.docx
| Day before symposium final information | 2022_Symposium/Email_Templates/SymposiumFinalInformation.docx
| Informtion with attachment about parking and lodging near symposium | 2022_Symposium/Email_Templates/SymposiumInformation.docx
| Thank you for your attendance, please fill out survey email | 2022_Symposium/Email_Templates/ThankYou_Survey.docx
General_Information | Template for making and printing name tags | 2022_Symposium/General_Information/Avery8521VerticalStyleNameBadges_KUGC_2022.doc
| Slide shown during coffee breaks during symposium | 2022_Symposium/General_Information/BackgroundSlide.pptx
| Final breakdown of budget | 2022_Symposium/General_Information/Final_Budget.xlsx
| Checklist of items for venue and food | 2022_Symposium/General_Information/Generic_Venue_Checklist_060722.docx
| Giant check presented to award winners, printed at fedex | 2022_Symposium/General_Information/GiantCheck.xlsx
| Information about venue, parking, hotels, and a map with links | 2022_Symposium/General_Information/KUCG_2022Symposium_InfoSheet.pdf
| Final program booklet | 2022_Symposium/General_Information/KUCG_Program_Normal.pdf
| Final program booklet, editable | 2022_Symposium/General_Information/KUCG_Program.docx
| Final program schedule | 2022_Symposium/General_Information/KUCG_Program.xlsx
| Map of downtown area with restaurants, hotels, venue, and parking | 2022_Symposium/General_Information/KUCGSymposiumMapC.pdf
| Maceli's menu | 2022_Symposium/General_Information/Macelis_Menu.pdf
| Maceli's quote | 2022_Symposium/General_Information/Macelis_Quote_011922.pdf
| Instructions to create an interactive map | 2022_Symposium/General_Information/MAP_README.txt
| Pumping station information | 2022_Symposium/General_Information/Pumping_Station.docx
| QR Code to link to symposium site | 2022_Symposium/General_Information/QRCodeSymposiumSite.png
| Registration questions and abstract submission info | 2022_Symposium/General_Information/Registration_Questions.docx
| Printout for speakers with instructions | 2022_Symposium/General_Information/Speaker_Guide.docx
| Symposium flyer | 2022_Symposium/General_Information/SymposiumFlyer.pdf
Keynote_Speaker | List of potential speakers and voting | 2022_Symposium/Keynote_Speaker/InvitedSpeaker_CandidateList.csv
| W9 form for honorarium | 2022_Symposium/Keynote_Speaker/IRS_W9.pdf
| Contact information for KU and Airport Transportation | 2022_Symposium/Keynote_Speaker/Keynote_Coordinating_Contact_Info.docx
| Keynote invitation to speak | 2022_Symposium/Keynote_Speaker/KUCG_Keynote_Invite_Template.docx
| Contractual services for for honorarium | 2022_Symposium/Keynote_Speaker/kcur-contractural-services-form-072621.pdf
| Information requested from keynote for coordination of travel | 2022_Symposium/Keynote_Speaker/Requested_Keynote_Info.docx
| Keynote schedule | 2022_Symposium/Keynote_Speaker/Schedule.xlsx
Organizer_Contact_Info.md | Names of KUCG organizers and KU contacts | 2022_Symposium/Organizer_Contact_Info.md
Post_Symposium_Survey | Survey questions | 2022_Symposium/Post_Symposium_Survey/KUCG_symposium_survey_final.docx
| Survey responses | 2022_Symposium/Post_Symposium_Survey/KUCG2022Symposium_Survey20220526.xlsx
Posters | Poster number assignments | 2022_Symposium/Posters/KUCG_Poster_Numbers_2022.xlsx
| Poster numbers and abstracts | 2022_Symposium/Posters/KUCG_Posters_051122.xlsx
| Poster numbers for printing and cutting out | 2022_Symposium/Posters/Poster_numbers.docx
| Poster judging template | 2022_Symposium/Posters/PosterJudging_Prelim.xlsx
| Poster judging rubric | 2022_Symposium/Posters/Symposium_poster_rubric_QRcode.docx
Talks | Accepted talks, titles, abstracts | 2022_Symposium/Talks/AcceptedTalks.docx
| Talk judging results | 2022_Symposium/Talks/KUCG_Talk_Judging_Results.csv
| Talk judging rubruc | 2022_Symposium/Talks/Symposium_talk_rubric_QRcode.csv
| All submitted talk abstracts | 2022_Symposium/Talks/TalkAbstracts_Voting.xlsx
| Notes on what could be improved and what went well at the 2022 symposium | 2022_Symposium/Debrief_Notes.docx